## Slide 1
EXECUTIVE BRIEFING
AWS Cloud Migration Strategy
SLZ 2.0
RLZ
From Santander Landing Zone v2 to Regional Landing Zone
March 20, 2026
Prepared for CTO Leadership Board
CTO Team — Cloud Platform & RLZ Program
Confidential | Internal Use Only

## Slide 2
AGENDA
AWS Cloud Migration: SLZ 2.0 → RLZ
CTO Team — Cloud Platform & RLZ Program
2
1
Context & Migration Overview
Strategic drivers & workflow phases
2
Key Points to Consider
Mandatory RLZ requirements
3
Phase 1: Project Assessment
Planning & gap analysis
4
Phase 2: Adaptation & Onboarding
Refactoring & deployment
5
Phase 3: Go Live
Cutover & validation
6
Next Steps
Governance & immediate actions
7
Projects Accounts Inventory
Current migration scope
CTO Team — Cloud Platform & RLZ Program
2

## Slide 3
Context | Migrate from SLZ 2.0 to RLZ
Strategic Overview
Why Migrate Now?
Critical Driver
RLZ introduces a radically new network model and RBAC model. The previous migration methods used for SLZ 4.0 are incompatible with these structural changes.
Viable Path
The only sustainable approach is to re-deploy projects directly on RLZ infrastructure and perform a controlled migration or copy of the data.
Migration Workflow Strategy
Project
Assessment
Project
Adaptation
RLZ
Onboarding
RLZ
Deployment
Data
Migration
Validation
& Cutover
PHASE 1
PHASE 2
PHASE 3
CTO Team — Cloud Platform & RLZ Program
3

## Slide 4
Key Points to Consider
The RLZ defines the following mandatory requirements for migration:
VPC Configuration
Only one VPC is permitted per account and region to maintain strict network isolation standards.
Network CIDR Validation
GSNet Routable: 180.x.x.x / 107.x.x.x
Private Non-routable: 10.x.x.x (Local only)
IaC Automation Roles
Account Automation roles are restricted and only usable via authorized tools: Gluon, GitHub, TFE Global, Quicksilver.
Authentication Standards
No Access/Secret Keys allowed. Must use OIDC configuration. Exceptions are strictly limited.
Service Accessibility
All deployed services must be accessible via AWS Public Endpoints rather than private VPC endpoints where possible.
Internet Egress
All accounts are provisioned with Internet access restricted to an authorized allow-list of external sites.
Global PCA Availability
Private Certificate Authority (PCA) is available as a Global shared service accessible to all RLZ accounts.
Boundary Policy Restrictions
Certain administrative actions and permissions are explicitly limited by the new RLZ Boundary Policies.
CTO Team — Cloud Platform & RLZ Program
4

## Slide 5
Workflow Proposal | Project Assessment
PHASE 1
Define Adaptation Plan
Establish roadmap to adapt configurations to new RLZ standards
1
Identify Restricted Configs
Catalog configurations not permitted in RLZ environment
2
Select Migration Method
Determine strategy: Big Bang vs. Parallel Cutover
3
Data Copy Strategy
Choose method: Synchronization, Backup/Restore, or Snapshot
4
Verify IaC Automation
Confirm full automation of AWS service deployment & config
5
Firewall Rules Analysis
Identify and request necessary network flows and FW rules
6
IAM & Permissions
Map out required roles and permissions for the new account
7
CTO Team — Cloud Platform & RLZ Program
5

## Slide 6
Workflow Proposal | Adaptation & Onboarding
PHASE 2
RLZ Account Onboarding
Configure new IPs, Firewall rules, and IAM roles for the target environment
1
Pipeline Migration
Migrate to SCIB Gluon Components (independent/TFE) if not already using Gluon
2
Configuration Adaptation
Apply necessary changes identified during the assessment phase
3
Service Deployment
Deploy all AWS services to the new account using automated Gluon pipelines
4
Unitary Testing
Execute unit tests to verify individual service functionality
5
Data Migration
Perform initial data copy and establish synchronization mechanisms
6
Implementation Testing
Validate the full project implementation in the new RLZ environment
7
CTO Team — Cloud Platform & RLZ Program
6

## Slide 7
Workflow Proposal | Go Live
PHASE 3
Define Cutover Plan
Establish detailed migration sequence for the new RLZ account
1
Validation Plan
Prepare comprehensive testing criteria to verify success
2
Assert Production Config
Verify readiness: Monitoring, Backup policies, CMDB registration
3
Schedule Migration
Book the official maintenance window for production cutover
4
Execute & Validate
Perform migration steps and sign off on successful deployment
CTO Team — Cloud Platform & RLZ Program
7

## Slide 8
Next Steps
Immediate actions to initiate the migration program
Action Plan
01
Project Manager
Appoint a Project Manager to oversee the initiative, ensuring coordination across all teams and stakeholders.
02
Dedicated Owners
Assign a dedicated owner for each project to ensure clear accountability and direct communication channels.
03
Migration Priorities
Define and agree on migration priorities based on technical complexity, business criticality, and dependencies.
04
Working Sessions
Establish regular cross-team working sessions to track progress, resolve blockers, and share knowledge.
05
MASTER PLAN CONSOLIDATION
Consolidate all inputs into a comprehensive master plan covering detailed scope, timelines, inter-project dependencies, resource allocation, and budget requirements.
CTO Team — Cloud Platform & RLZ Program
8

## Slide 9
Projects Accounts Inventory
Migration Scope Overview & Environment Status
Total Scope
34 Projects
#
Application Name
APM / Owner
DEV
PRE
PRO
01
Origin
[Assignee]
✓
✓
✓
02
Darwin
[Assignee]
✓
✓
–
03
Hybrid Balancer
[Assignee]
✓
✓
✓
04
IBM API Connect CIB
[Assignee]
✓
✓
✓
05
OASIS
[Assignee]
✓
–
–
06
Fnality Connect
[Assignee]
✓
✓
✓
07
Athena
[Assignee]
✓
✓
✓
08
Sigom Evolution
[Assignee]
✓
✓
✓
09
MARS Cloud
[Assignee]
✓
✓
✓
10
MarketFit Cloud
[Assignee]
✓
✓
✓
11
Secfin
[Assignee]
✓
✓
✓
12
Grid AWS
[Assignee]
✓
✓
✓
13
Global Receivables
[Assignee]
✓
✓
✓
14
DaaS Governance Tool
[Assignee]
✓
–
–
15
DUNE
[Assignee]
✓
✓
✓
16
Murex 3.1 Europe
[Assignee]
✓
✓
✓
17
Baltra Curve Server
[Assignee]
✓
✓
✓
18
Integrity Check
[Assignee]
✓
✓
✓
19
CIB HUB QlikSense
[Assignee]
✓
✓
✓
20
ORBE
[Assignee]
✓
✓
✓
21
Dynamic Discount
[Assignee]
✓
✓
✓
22
Titanium
[Assignee]
✓
✓
✓
23
KOLT
[Assignee]
✓
✓
✓
24
Collections
[Assignee]
✓
✓
✓
25
DOMINO
[Assignee]
✓
✓
✓
26
SAP Model Company
[Assignee]
✓
✓
✓
27
ForgeRock CIAM
[Assignee]
✓
✓
✓
28
DICTE
[Assignee]
✓
✓
✓
29
Retina
[Assignee]
✓
✓
✓
30
GTB AWS CROSS
[Assignee]
✓
✓
✓
31
Laboratorio CTO IAC
[Assignee]
✓
–
–
32
Laboratorio Produccion
[Assignee]
–
–
✓
33
Laboratorio Arcane
[Assignee]
✓
–
–
34
Laboratorio Auditoria
[Assignee]
✓
–
–
34 Total Applications
✓ Active Environment
– Not Applicable
* Scroll list to view all
CTO Team — Cloud Platform & RLZ Program
9

## Slide 10
Thank You.
Let's build the future of Santander Cloud Infrastructure together
QUESTIONS & DISCUSSION
Primary Contacts
CTO Team — Cloud Platform
RLZ Program Management
Technical Support
Gluon / TFE Global / Quicksilver
GitHub OIDC Integration
Santander Technology
CTO Team | Regional Landing Zone Migration | 2026